## Projects
ProjectID | ProjectName | OwningCompany | CustomerAccount | CalendarName | ContractingUnit | ProjectManager | ProjectStart
P09182026-1 | SP Project 01 | USPM | MWTestCustomer1 |  | Contoso Robotics US | Satish Panwar | 2026-07-06 09:00
P09182026-2 | SP Project 02 | USPM | MWTestCustomer1 |  | Contoso Robotics US | Satish Panwar | 2026-07-06 09:00

## Tasks
ProjectID | TaskKey | TaskName | ParentTaskKey | EffortHours | ScheduledStart | ScheduledEnd | OutlineLevel | ProjectBucket
P09182026-1 | A1 | A1 Initiation |  |  |  |  | 1
P09182026-1 | A1.1 | A1.1 child 01 | A1 | 10 | 2026-09-13 |  |  | PB2
P09182026-1 | A2 | A2 Initiation |  | 10 | 2026-09-13
P09182026-2 | A1 | A1 Initiation |  |  |  |  | 1
P09182026-2 | A1.1 | A1.1 child 01 | A1 | 5 | 2026-09-13 |  |  | PB2
P09182026-2 | A2 | A2 Initiation |  | 4 | 2026-09-13

## Assignments
ProjectID | AssignmentKey | TaskKey | ResourceName | RoleName
P09182026-1 | AK1 | A1.1 | Satish Panwar | Network Technician
P09182026-1 | AK2 | A1.1 | User1 | Network Technician
P09182026-1 | AK3 | A2 | User2 | Consulting Lead
P09182026-2 | AK1 | A1.1 | Martin Walker | Consulting Lead
P09182026-2 | AK2 | A1.1 | User1 | Network Technician
P09182026-2 | AK3 | A2 | User2 | Consulting Lead

## Dependencies
ProjectID | PredecessorTaskKey | SuccessorTaskKey | LinkType
P09182026-1 | A1 | A2 | FinishToStart
P09182026-2 | A1 | A2 | FinishToStart

## Instructions
Sheet | Purpose | Required keys
Projects | One row per project to create or reuse. | ProjectKey must be unique.
Tasks | One row per task. Use ParentTaskKey for WBS hierarchy. | ProjectKey + TaskKey must be unique.
Assignments | One row per task/resource assignment. | ProjectKey and TaskKey must exist.
Dependencies | One row per task dependency. | Predecessor/SuccessorTaskKey must exist in the same project.